## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 (Story ID-1,2,5) | Yes | Yes | High | In Progress | 14 | Yes
Task 1: Research sign language recognition module | Yes | Yes | High | Complete | 3 | Yes
Task 2: Develop algorithm for converting sign language gestures to text | Yes | Yes | High | Complete | 8 | Yes
Task 3: Design user interface for sign language recognition feature | Yes | Yes | Medium | Complete | 3 | Yes
Sprint 5 (Story ID-3,4,6) | Yes | No | High | In Progress | 18 | Yes
Task 4: Integrate sign language recognition module with the virtual meet platform | Yes | No | High | In Progress | 5 | Yes
Task 5: Implement real-time translation of sign language gestures into text | Yes | Yes | High | In Progress | 8 | Yes
Task 6: Integration testing with virtual meeting platforms | Yes | No | High | Not Started | 5 | Yes | l;
Sprint 2 (Story ID-2,3) | Yes | No | Medium | In Progress | 13 | Yes
Task 7: Test accuracy and reliability of sign language recognition feature | Yes | Yes | High | Complete | 5 | Yes
Task 8: Conduct usability testing for sign language recognition feature | Yes | No | Medium | In Progress | 5 | Yes
Task 9: User testing for seamless integration experience | Yes | No | Medium | Not Started | 3 | Yes
Sprint 4 (Story ID-7,8) | Yes | Yes | Medium | In Progress | 4 | Yes
Task 10: Documentation for sign language recognition feature | Yes | Yes | Medium | Complete | 2 | Yes
Task 11: Documentation for virtual meeting platform integration | Yes | Yes | Medium | Complete | 2 | Yes
Sprint 3 (Story ID-9) | Yes | Yes | High | Complete | 9 | Yes
Task 12: Implement Join Meeting functionality | Yes | Yes | High | Complete | 3 | Yes
Task 13: Implement Leave Meeting functionality | Yes | Yes | High | Complete | 3 | Yes
Task 14: Implement Create Meeting functionality | Yes | Yes | High | Complete | 3 | Yes
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started