## Sheet1
Agile Test Plan
Project Name | Inclusive Virtual Meeting Platform |  | Browser: | Platform Compatibility
Test Case ID | IVMP-S1-T1 |  | Version: | 1.4
Written By: | Ritik kumar and Anuj Taparia |  | Description: | Test the symbol-to-text conversion functionality in the virtual meeting platform.
Tested By: | Ritik kumar and Anuj Taparia |  | Tested On: | 2024-04-18
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2024-02-23 | Input various symbols or gestures into the platform. | Symbols or gestures are accurately converted into text. | Symbols and gestures are accurately converted into text, including common signs such as alphabets, some times not giving the accurate or expected result.
2 | 2024-02-23 | Verify that the converted text is displayed in real-time. | The converted text is displayed promptly within the meeting interface. | Implemented this feature yet but the accuracy is low.
3 | 2024-03-08 | UI for the Virtual Meet | The user friendly UI for the virtual meet. | Basic UI is made and ready for deployment but has yet to be integrated with the application
4 | 2024-03-08 | Testing of accuracy of our application | Good accuracy and streamless prediction. | The expected accuracy was not reached for the real time prediction of ASL but the testing images accuracy was reached.
5 |  | Integration of the UI and application | After Integrating both works streamlessly and without defect.
6 |  | Testing of UI | The UI can host a lot of people at the same time without affecting proficiency.
Create a Test Plan in Smartsheet

## Sheet2
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE